## Sprint Backlog
Pathivara Website — Sprint Backlog (Sprint 1–5)
Sprint | Task / Backlog Item | Category | Priority | Est. Points | Status
Sprint 1 — Foundation & Auth
Sprint 1 | Language selection screen (English/Nepali) on first launch | Onboarding | High | 3 | To Do
Sprint 1 | Phone number login page with OTP/SMS password recovery | Auth | High | 5 | To Do
Sprint 1 | Buyer registration form (name, phone, password) | Auth | High | 3 | To Do
Sprint 1 | Account type selector: Household vs Shop/Bulk Buyer | Auth | High | 2 | To Do
Sprint 1 | Guest browse mode — catalogue accessible without login | Auth | Medium | 2 | To Do
Sprint 1 | Homepage layout: Browse, Products, My Orders, Track Order CTAs | Navigation | High | 3 | To Do
Sprint 1 | My Orders link in top navigation bar | Navigation | Medium | 1 | To Do
Sprint 1 | Notification permission requested after login (not on launch) | Auth | Low | 1 | To Do
Sprint 2 — Product Catalogue & Search
Sprint 2 | Nepali & local-alias product search (Tori Tel → mustard oil) | Search | High | 5 | To Do
Sprint 2 | Product listing cards: image, name, price, stock badge | Catalogue | High | 3 | To Do
Sprint 2 | Stock badge on every card: In Stock / Low Stock / Out of Stock | Catalogue | High | 2 | To Do
Sprint 2 | Notify Me button on out-of-stock product pages | Catalogue | Medium | 2 | To Do
Sprint 2 | Filter panel: category + unit size on listing page | Catalogue | Medium | 3 | To Do
Sprint 2 | Product detail page: official photos + accurate details | Catalogue | High | 3 | To Do
Sprint 2 | Volume discount tiers (0–9 / 10–49 / 50+) on product detail | Catalogue | High | 3 | To Do
Sprint 2 | Structured specification table (grade, unit, pack count, shelf life) | Catalogue | Medium | 2 | To Do
Sprint 2 | 30-day price history sparkline on staple product pages | Catalogue | Medium | 3 | To Do
Sprint 3 — Cart & Checkout
Sprint 3 | Pathivara trust/guarantee banner visible before checkout | Cart | Medium | 1 | To Do
Sprint 3 | Price-change alert in cart when item price updates | Cart | High | 3 | To Do
Sprint 3 | Bulk discount total + final total in cart summary | Cart | High | 2 | To Do
Sprint 3 | Plus/minus qty stepper on each cart row (no reload) | Cart | High | 2 | To Do
Sprint 3 | Progress bar in cart: units needed to reach next discount tier | Cart | Medium | 2 | To Do
Sprint 3 | Save cart as named Basket template | Cart | Medium | 3 | To Do
Sprint 3 | Single-page checkout: contact, pickup slot, payment, confirmation | Checkout | High | 5 | To Do
Sprint 3 | Pre-fill saved name + phone at checkout for returning buyers | Checkout | Medium | 1 | To Do
Sprint 3 | Fixed pickup slot selector at checkout | Checkout | High | 2 | To Do
Sprint 3 | Checkout order summary: subtotal, discount, tax, total due | Checkout | High | 2 | To Do
Sprint 3 | Free-text order notes field on checkout page | Checkout | Low | 1 | To Do
Sprint 4 — Payment, Tracking & Orders
Sprint 4 | Pay at Pickup payment method option | Payment | High | 2 | To Do
Sprint 4 | Digital Transfer / QR Payment option at checkout | Payment | High | 2 | To Do
Sprint 4 | Upload payment screenshot or enter transaction ID | Payment | High | 3 | To Do
Sprint 4 | "Payment Proof Submitted" state while shop verifies transfer | Payment | Medium | 2 | To Do
Sprint 4 | Payment status badge: Pending → Confirmed after verification | Payment | Medium | 2 | To Do
Sprint 4 | WhatsApp/SMS confirmation immediately after order placed | Notifications | High | 3 | To Do
Sprint 4 | Push notification + SMS when vendor accepts order | Notifications | Medium | 2 | To Do
Sprint 4 | SMS when order is ready for pickup | Notifications | High | 2 | To Do
Sprint 4 | Order tracking: Placed → Acknowledged → Ready → Collected stages | Order Tracking | High | 3 | To Do
Sprint 4 | Payment status displayed separately from order status on tracking | Order Tracking | Medium | 1 | To Do
Sprint 4 | My Orders: past orders with status, item summary, payment, total | Order History | High | 3 | To Do
Sprint 4 | Order Again button rebuilds past order at current prices | Order History | Medium | 2 | To Do
Sprint 4 | PDF receipt download immediately after order confirmation | Order History | Medium | 3 | To Do
Sprint 5 — Wholesale, Baskets, Disputes & Polish
Sprint 5 | Wholesale access request form (shop name, area, business type) | Wholesale | High | 3 | To Do
Sprint 5 | "Wholesale Request Pending" badge on buyer account page | Wholesale | Medium | 1 | To Do
Sprint 5 | "Verified Wholesale Buyer" badge + wholesale pricing activated | Wholesale | High | 2 | To Do
Sprint 5 | Bulk discounts visible on product page before adding to cart | Wholesale | Medium | 2 | To Do
Sprint 5 | Load saved Basket from My Orders directly into cart | Baskets | Medium | 2 | To Do
Sprint 5 | Stock + price change review before Basket goes to cart | Baskets | Medium | 2 | To Do
Sprint 5 | Structured complaint/dispute flow with photo upload option | Support | Medium | 3 | To Do
Sprint 5 | Cross-browser + mobile responsive QA pass (all screens) | QA & Polish | High | 3 | To Do

## Sprint Summary
Pathivara Website — Sprint Summary
Sprint | Theme | Sprint Goal | Key Deliverables | Story Points | User Stories
1 | Foundation & Auth | User can register, log in, choose language, and browse as guest | Language toggle, phone login + recovery, registration form, buyer type selector, guest browse, homepage layout, bottom nav | 8 | 8
2 | Product Catalogue & Search | User can search, browse, and inspect any product including price history | Nepali search aliases, product listing grid, stock badges, Notify Me, filter panel, product detail page, discount tiers, spec table, sparkline | 26 | 9
3 | Cart & Checkout | User can manage cart and complete a full single-page checkout | Price-change alert, bulk discount total, qty stepper, discount progress bar, save basket, single-page checkout, pickup slot selector, order summary, notes field | 23 | 9
4 | Payment, Tracking & Orders | User can pay, track order progress, and view order history | Pay at Pickup, QR/Digital Transfer, proof upload, payment status badges, WhatsApp/SMS confirmations, order tracking stepper, My Orders list, Order Again, PDF receipt | 27 | 13
5 | Wholesale, Baskets & Polish | Wholesale flow complete; baskets + disputes working; site QA passed | Wholesale request form + badges, bulk pricing for wholesale, basket load + diff review, complaint flow, cross-browser QA, accessibility audit, Lighthouse perf check, persona walkthrough | 24 | 10
TOTAL (5 Sprints) |  |  |  | 108 | 49